## Sheet1
CRT Team- Sprintwise
| Activities | BA | QA | Dev. | PM
DAY 1 | Sprint Kickoff call (For Mobile) | ü | ü | ü | ü
| Ticket Analysis | ü | ü | ü | ü
| Development |  |  | ü
| Status Call (Alternate Days) |  | ü |  | ü
DAY 2 | Ticket Analysis | ü | ü |  |  | PM | QA | Dev. | BA
| Development |  |  | ü |  | Dinesh | Avinash | Saurabh | Zamaan
DAY 3 | Ticket Analysis | ü | ü |  |  |  |  | Anuja
| Development |  |  | ü |  |  |  | Pranit
| Status Call (Alternate Days) |  | ü |  | ü
DAY 4 | Ticket Analysis | ü | ü
| Development |  |  | ü
| Status Call (Alternate Days) |  | ü |  | ü
DAY 5 | Ticket Analysis | ü
| Development (Release Internal Build) |  |  |  | ü
| Testing/ Verification | ü | ü
DAY 6, 7, 8 | Ticket Analysis | ü
| Bug fixing |  |  | ü
| Status Call (Alternate Days) |  | ü |  | ü
| Testing/ Verification | ü | ü
DAY 9 | Bug fixing |  |  | ü
| Status Call (Alternate Days) |  | ü |  | ü
| Testing/ Verification | ü | ü
DAY 10 | Internal Release to AHM | ü | ü | ü | ü
| Ticket analysis for next sprint | ü | ü | ü
| Testing/ Verification | ü | ü
DAY 11, 12, 13, 14 | Ticket analysis for next sprint | ü | ü | ü
| Bug fixing (issues from AHM in Internal Build) | ü | ü | ü | ü
| Status Call (Alternate Days) |  | ü |  | ü
| Testing/ Verification | ü | ü
DAY 15 | Release build to client with resolved issues from AHM | ü | ü | ü | ü
| Ticket analysis for next sprint | ü
| Testing/ Verification | ü | ü