## Sheet1
Day | Tasks Team | Dev | QA | BA | Lead
Day 1 | Sprint Kick Off Call | ü | ü | ü | ü | Dev | Lead | BA | QA
| Tickets Analysis |  |  | ü | ü | Pota | Samata | Samata | Veerdhawal
| Add PE approach |  |  |  | ü | Maruf | Hetal | Veerdhawal | Samata
| Development | ü |  |  |  | Hetal
| Daily Stand up | ü | ü | ü | ü | Pankaj
Day 2 | Tickets Analysis |  |  | ü | ü
| Adding PE Approach |  |  |  | ü | Note: Final QA is done by Comity team.
| Daily Stand Up | ü | ü | ü | ü
| Development/Unit Testing | ü
| Daily Status Call |  |  | ü | ü
Day 3 | Daily Stand Up | ü | ü | ü | ü
| Development/Unit Testing | ü
| Tickets Analysis |  |  | ü | ü
| Testing/Verification |  | ü
Day 4, 5, 6 | Daily Stand Up | ü | ü | ü | ü
| Development/Unit Testing | ü
| Tickets Analysis |  |  | ü | ü
| Testing/Verification |  | ü
| Daily Status Calls |  |  | ü | ü
Day 7 | Daily Stand Up | ü | ü | ü | ü
| Development/Unit Testing | ü
| Testing/Verification |  | ü
| Daily Status Calls |  |  | ü | ü
| Release Notes Preparation | ü
| Release Notes Review |  |  | ü | ü
| Demo Video Preparation |  |  | ü
| Tickets Analysis for Next Sprint |  |  | ü | ü
Day 8 | Daily Stand Up | ü | ü | ü | ü
| Development/Bug Fixing/UT | ü
| Testing/Verification |  | ü
| Release Notes Preparation | ü
| Release Notes Review |  |  | ü | ü
| Demo Video Preparation |  |  | ü
| Tickets Analysis for Next Sprint |  |  | ü | ü
Day 9, 10 | Daily Stand Up | ü | ü | ü | ü
| Bug Fixing/UT | ü
| Testing/Verification |  | ü
| Daily Status Calls |  |  | ü | ü
| Release Notes Preparation | ü
| Release Notes Review |  |  | ü | ü
| Demo Video Preparation |  |  | ü
| Tickets Analysis for Next Sprint |  |  | ü | ü
| Adding PE Approach |  |  |  | ü